TONIC SOL-FA (“TSF”)

Twelve Week Marketing Plan (2009)

| 12 WEEKS OUT: (___________) Date | - Recruit publicity team. Find motivated individuals willing to make this show a successful event. - Make a publicity plan and formulate goals to achieve agreed upon plan. The TSF Twelve Week Marketing Plan is a great place to start! - Meet with all sponsors, concert and promotion committees regarding the upcoming publicity campaign. - Contact Tonic Sol-fa regarding any promotional needs. Check the TSF Media Page (log-in code: rescued) at www.tonicsolfa.com for numerous promotional items available for download. |
| --- | --- |

| 11 WEEKS OUT: (___________) | - Distribute tickets to outlets for immediate sale (utilize www.tonicsolfa.com for online ticket sales). |
| --- | --- |
| - 10 WEEKS OUT: - (___________) - ***THE 10th WEEK IS VITALLY IMPORTANT TO THE SUCCESS OF ALL OF TSF'S SELF-PRODUCED CONCERTS. THIS WEEK INVOLVES A LOT OF WORK, BUT THE RESULTS HAVE BEEN EXTRAORDINARY. PLEASE READ WITH CARE*** | Radio - Contact all radio formats within a 25 mile radius. Utilize a popular station as a "main" sponsor, others as secondary. Contemporary, Country, Oldies, Rock, Talk, etc., all work well. For sponsoring ("main") station: - Plan a station visit using a member of the publicity team or Tonic Sol-fa, if possible. Phone interviews are a great alternative. Visits will help motivate station personnel and encourage interest in your event. - Initiate contests. Use tickets and/or TSF CDs as giveaways (suggested - five pairs of tickets/five CDs). - Schedule ads and on-air mentions (suggested minimum - five per day). Ads are available on the TSF Media Page. Exchange tickets for ads if necessary. - Add show date to all community calendars. - Ask on-air personality to emcee show. - Invite station personnel to attend show (again, their interest can help your event even after it's finished). For secondary stations: - Plan phone-in interviews. - Schedule mentions, if possible. - Add show date to all community calendars. Newspaper/Print Media - Contact at least three publications (main papers, shoppers, area magazines, high school/college publications, etc.) within a 25 mile radius. - Plan a personal interview using a member of the publicity team and/or TSF. - Schedule two feature articles (preferably with a picture) in an Entertainment or equally suitable section of the publication. - Add show date to all community calendars. - Schedule ad placement. Ads are available on the TSF Media Page. Exchange tickets for ads if necessary. - Invite entertainment personnel to the show to cover the event. Television (if applicable) - Plan station visit(s) (morning and/or evening) with all local affiliates using a member of the publicity team and/or TSF, if routing permits. - Schedule ads. Ads are available on the TSF Media Page (please confirm format). - Utilize area school’s closed-circuit TV, if available. - Invite TV personnel to attend the show. |
|  | Sponsorship - Find single/multiple corporate sponsors to alleviate publicity costs. Programs, logo placement, stage mentions, etc., may all be used to promote business sponsor(s) in exchange for financial/other help said business may provide. - Contact groups, clubs, businesses, etc., for discounted ticket prices and/or pre-sale tickets (suggested - blocks of 20 or more). Web/Email - Utilize TSF's email list to send concert info to potential ticket buyers in your area. A direct mailing is also available for a fee. - Contact Chamber of Commerce, Department of Tourism or other local/state groups to help "spread the word." Plan a link to their sites, email lists or online calendars. - If applicable, link your event’s website to www.tonicsolfa.com. - Begin sending regular emails to your own database if applicable with links to ticket details and www.tonicsolfa.com. - Market through your Facebook community, mobilize a Twitter campaign, or begin to utilize YouTube’s reach in a creative/personal way within the coming weeks. (A regular blog, vlog, etc. may be the best tool to reach your audience where they shop and play). Other - Plan high school/college choir visits or announcements using a member of the publicity team or Tonic Sol-fa, if routing permits. Advise directors of group discounts and possible student seller campaigns (contact TSF for specifics). Send video/CD and poster to raise interest. - Print flyers to hand out at local events and/or design table tents to be placed in local restaurants. Please approve artwork with TSF. - Approach high school/community choirs to open for Tonic Sol-fa (suggested opening slot - fifteen minutes). |
| - 9 WEEKS OUT: - (___________) | - Web/Email - Check www.tonicsolfa.com to be sure the calendar (and store) is updated with your show's tickets, location, dates, etc. Email any additional corrections to Laurel at tonicsol@aol.com. - Continue your efforts with Facebook, Twitter, and the like. - Place posters in high-traffic areas (schools, grocery stores, churches, gas stations, banks, coffee shops, etc.). |
| - 8 WEEKS OUT: - (___________) | - Radio - Confirm mentions and calendars. - Newspaper/Print Media - Place first ads. - Television - Begin all commercials. - Web/Email - Link to all available websites. - Use social marketing networks to promote a contest aimed to increase interest and visibility of the upcoming conert. |
| - 6 WEEKS OUT: - (___________) | - Web/Email - Contact TSF to send a mass email to potential ticket buyers. Again, a direct mailing is also available for a fee. - Check poster wear and tear at all locations. - Hand out flyers and/or place table tents. |
| - 5 WEEKS OUT: - (___________) | - Radio - Begin ad blitz. - Newspaper/Print Media - Confirm mentions and calendars. - Television - Monitor stations. - Sponsorship - Continue block ticket selling to groups. - Begin to keep a weekly ticket count. This count will allow you to see more clearly what publicity may still be needed (not every town is a "walk-up" town and early sell-outs create future buzz). A ticket count sheet is available for use on the TSF Media Page. |
| - 4 WEEKS OUT: - (___________) | - Newspaper/Print Media - Confirm 1st cover story to run next week. |
| - 3 WEEKS OUT: - (___________) | - Web/Email - Send a follow-up mass email and/or direct mailing. - Begin a final, massive appeal for the next seven days utilizing all available internet portals in your campaign. |
| - 2 WEEKS OUT: - (___________) | - Newspaper/Print Media - Confirm 2nd cover story to run next week. |
| - 1 WEEK OUT: - (___________) | - Radio - Add giveaways if needed. - Finalize group ticket sales. - Pick up all tickets and monies at outlets. - Sell tickets at the door, if necessary. - Give remaining tickets to underprivileged community groups, if desired. - Let TSF know what worked or did not work for you. - ENJOY YOURSELF AT THE CONCERT! |