TONIC SOL-FA (“TSF”)

Twelve Week Marketing Plan (2009)

| 12 WEEKS OUT: (___________) Date | Recruit publicity team. Find motivated individuals willing to make this show a successful event. Make a publicity plan and formulate goals to achieve agreed upon plan. The TSF Twelve Week Marketing Plan is a great place to start! Meet with all sponsors, concert and promotion committees regarding the upcoming publicity campaign. Contact Tonic Sol-fa regarding any promotional needs. Check the TSF Media Page (log-in code: rescued) at www.tonicsolfa.com for numerous promotional items available for download. |
| --- | --- |

| 11 WEEKS OUT: (___________) | Distribute tickets to outlets for immediate sale (utilize www.tonicsolfa.com for online ticket sales). |
| --- | --- |
| 10 WEEKS OUT: (___________) ***THE 10th WEEK IS VITALLY IMPORTANT TO THE SUCCESS OF ALL OF TSF'S SELF-PRODUCED CONCERTS. THIS WEEK INVOLVES A LOT OF WORK, BUT THE RESULTS HAVE BEEN EXTRAORDINARY. PLEASE READ WITH CARE*** | Radio Contact all radio formats within a 25 mile radius. Utilize a popular station as a "main" sponsor, others as secondary. Contemporary, Country, Oldies, Rock, Talk, etc., all work well. For sponsoring ("main") station: Plan a station visit using a member of the publicity team or Tonic Sol-fa, if possible. Phone interviews are a great alternative. Visits will help motivate station personnel and encourage interest in your event. Initiate contests. Use tickets and/or TSF CDs as giveaways (suggested - five pairs of tickets/five CDs). Schedule ads and on-air mentions (suggested minimum - five per day). Ads are available on the TSF Media Page. Exchange tickets for ads if necessary. Add show date to all community calendars. Ask on-air personality to emcee show. Invite station personnel to attend show (again, their interest can help your event even after it's finished). For secondary stations: Plan phone-in interviews. Schedule mentions, if possible. Add show date to all community calendars. Newspaper/Print Media Contact at least three publications (main papers, shoppers, area magazines, high school/college publications, etc.) within a 25 mile radius. Plan a personal interview using a member of the publicity team and/or TSF. Schedule two feature articles (preferably with a picture) in an Entertainment or equally suitable section of the publication. Add show date to all community calendars. Schedule ad placement. Ads are available on the TSF Media Page. Exchange tickets for ads if necessary. Invite entertainment personnel to the show to cover the event. Television (if applicable) Plan station visit(s) (morning and/or evening) with all local affiliates using a member of the publicity team and/or TSF, if routing permits. Schedule ads. Ads are available on the TSF Media Page (please confirm format). Utilize area school’s closed-circuit TV, if available. Invite TV personnel to attend the show. |
|  | Sponsorship Find single/multiple corporate sponsors to alleviate publicity costs. Programs, logo placement, stage mentions, etc., may all be used to promote business sponsor(s) in exchange for financial/other help said business may provide. Contact groups, clubs, businesses, etc., for discounted ticket prices and/or pre-sale tickets (suggested - blocks of 20 or more). Web/Email Utilize TSF's email list to send concert info to potential ticket buyers in your area. A direct mailing is also available for a fee. Contact Chamber of Commerce, Department of Tourism or other local/state groups to help "spread the word." Plan a link to their sites, email lists or online calendars. If applicable, link your event’s website to www.tonicsolfa.com. Begin sending regular emails to your own database if applicable with links to ticket details and www.tonicsolfa.com. Market through your Facebook community, mobilize a Twitter campaign, or begin to utilize YouTube’s reach in a creative/personal way within the coming weeks. (A regular blog, vlog, etc. may be the best tool to reach your audience where they shop and play). Other Plan high school/college choir visits or announcements using a member of the publicity team or Tonic Sol-fa, if routing permits. Advise directors of group discounts and possible student seller campaigns (contact TSF for specifics). Send video/CD and poster to raise interest. Print flyers to hand out at local events and/or design table tents to be placed in local restaurants. Please approve artwork with TSF. Approach high school/community choirs to open for Tonic Sol-fa (suggested opening slot - fifteen minutes). |
| 9 WEEKS OUT: (___________) | Web/Email - Check www.tonicsolfa.com to be sure the calendar (and store) is updated with your show's tickets, location, dates, etc. Email any additional corrections to Laurel at tonicsol@aol.com. Continue your efforts with Facebook, Twitter, and the like. Place posters in high-traffic areas (schools, grocery stores, churches, gas stations, banks, coffee shops, etc.). |
| 8 WEEKS OUT: (___________) | Radio - Confirm mentions and calendars. Newspaper/Print Media - Place first ads. Television - Begin all commercials. Web/Email - Link to all available websites. Use social marketing networks to promote a contest aimed to increase interest and visibility of the upcoming conert. |
| 6 WEEKS OUT: (___________) | Web/Email - Contact TSF to send a mass email to potential ticket buyers. Again, a direct mailing is also available for a fee. Check poster wear and tear at all locations. Hand out flyers and/or place table tents. |
| 5 WEEKS OUT: (___________) | Radio - Begin ad blitz. Newspaper/Print Media - Confirm mentions and calendars. Television - Monitor stations. Sponsorship - Continue block ticket selling to groups. Begin to keep a weekly ticket count. This count will allow you to see more clearly what publicity may still be needed (not every town is a "walk-up" town and early sell-outs create future buzz). A ticket count sheet is available for use on the TSF Media Page. |
| 4 WEEKS OUT: (___________) | Newspaper/Print Media - Confirm 1st cover story to run next week. |
| 3 WEEKS OUT: (___________) | Web/Email - Send a follow-up mass email and/or direct mailing. Begin a final, massive appeal for the next seven days utilizing all available internet portals in your campaign. |
| 2 WEEKS OUT: (___________) | Newspaper/Print Media - Confirm 2nd cover story to run next week. |
| 1 WEEK OUT: (___________) | Radio - Add giveaways if needed. Finalize group ticket sales. Pick up all tickets and monies at outlets. Sell tickets at the door, if necessary. Give remaining tickets to underprivileged community groups, if desired. Let TSF know what worked or did not work for you. ENJOY YOURSELF AT THE CONCERT! |