## How To Use This Worksheet
The 7 Stages of Website Redesign
This Website Redesign Checklist will let you essentially function as the PM (Project Manager) for your website's redesign. The checklist is designed to walk a marketer through a redesign step-by-step from strategy to planning, designing, building, testing, and optimizing, to delivery, launch, promotion and final analysis. To make this checklist easier to use, this cover sheet will break down how to use each stage within the template for maximum productivity.
Stage I - Strategy
Developing a strategy ahead of time is an important part. Please read through the ebook portion of the redesign guide for detailed tips. As you approach your goals, be sure to tie your goals to measurable results. Some sample goals include increasing monthly traffic, making content more shareable, or improving conversion rates.
Stage II - Plan
Be sure to take the time to answer some crucial questions and evaluate whether you are doing this in-house or hiring someone to do the work. You should also take time to review all of your current assets - and, we mean all of your assets - page by page. This will take a lot of time and can easily be started as part of the first stage and may continue well in stage 4 and/or 5.
Stage III - Design
Throughout the design stage you and your designer should be in constant communication but note that a lot of back and forth at this point will effect your timeline. This stage is also an opportunity for you to continue to work on content and marketing planning especially as it relates to the site launch. To get the most out of the new design, all elements should work in harmony with marketing (i.e. content and call-to-action) best practices.
Stage IV - Build
The building stage is pretty much outside of your realm of work and entirely in the designer and/or developer's hands - this is where actual coding starts to take place. Use this time to finalize your content and prepare for the upcoming launch. Typically getting the site from 0-80% happens rather quickly, it's the remaining 20% that will take longer. The more you go back and forth with your designer and pick on small details, the longer this process will take.
Stage V - Optimize, Test and Deliver
This is the stage when your team should be all hands on deck. Everyone should do a run through of the site using different computers and browsers, reading the content, clicking around, filling out forms etc. Once all those parts have been explored and everything checks out, the site will be ready for full deployment. Have management sign off on everything, finalize content and schedule the site launch date.
Stage VI - Launch
Launching can mean different things to different people, mostly because there are various content management systems and development circumstances out there. For instance, if you are redesigning a site that uses a content management system or publishing platform, your launch may be as simple as applying a new theme. Consider launching site at off peak hours (especially if you have customer log-ins) and non-event days, just in case something goes wrong. Promoting the launch of your new site is optional. Depending on the types of changes it may not be worthwhile making a large announcement.
Stage VII - Analyze
Post-redesign analysis is important. You put all this time and money into this process, you'll want to know if it was worth it. Based on your goals and initial benchmarks, you'll want to do a before and after comparison. Collect the same benchmarks 1, 3 and 6 months after your redesign. It may take a few weeks, and in some cases months, to get back to previous performance, so don't be dissuaded if your site isn't performing as expected.
by
WEBSITE REDESIGN CHECKLIST
Note:
* While this checklist is thorough, it is not exhaustive.
* The exact processes and stages may vary from designer to designer so use this as a guideline and checklist to keep yourself on track.
* Set realistic expectations -- a redesign will not magically turn your website into a money tree.
* Due to its time intensive investment, a redesign should not divert you from your day-to-day marketing activities. It's important that during a redesign you still maintain business as usual and publish regular volumes of content.
Simplify your redesign process by using a professional CMS like those offered by the HubSpot Software. Learn how with a free personal demo!
How to Use this Progress Worksheet:
This template is meant for tracking your website redesign progress. We've divided each stage of a website redesign, as described to the left, into specific steps to help complete that stage. To help keep you on schedule, use the tracking sheet (second tab below) to see how much you've accomplished towards your ultimate redesign. The legend to the upper right of the sheet provides three options -- 5, 3, or 1. Each represents a point value and color. By entering these values into each step as it's completed, you are automatically changing the color of that row to be either green, yellow or red, respective to each numerical value. This gives you a clear picture of how much has been done, and how much still needs to be done.

## Website Redesign Tracking Sheet
| Website Redesign Progress Worksheet | *Tracking Status (Column C)
|  | 5 | Done. Completed task or confirmed.
|  | 3 | In progress. Due date set.
|  | 1 | On hold, due date TBD or unsure.
Not Applicable. For reference only.
|  | Answer | Replace this field with your own answers.
*To apply a tracking status simply manually enter 1, 3 or 5 (user whole numbers only) in column C where applicable or otherwise noted.
Update each item as the status and/or due date changes.
|  | *Tracking Status | Due Date | Date Completed | Owner(s)
|  | manually update | (mm/dd/yy) | (mm/dd/yy) | Who is responsible for this to be completed?
Stage I - Strategy
#1. Benchmark your current metrics.
Number of visits/visitors/unique visitors (monthly average). |  | Enter Stats
Bounce rate (monthly average). |  | Enter Stats
Time on site (monthly average). |  | Enter Stats
Top performing keywords (in terms of rank, traffic and lead generation). |  | Enter Stats
Number of inbound linking domains. |  | Enter Stats
Total number of new leads/form submissions (per month). |  | Enter Stats
Total amount of sales generated (per month). |  | Enter Stats
Total number of total pages indexed. |  | Enter Stats
Total number of pages that receive traffic. |  | Enter Stats
#2. Determine goal(s).
Why are you doing the redesign? |  | Replace w/ Answer
#3. Define your brand.
What is your business' message/unique value proposition? |  | Replace w/ Answer
Is it (message and/or branding) changing or staying the same? |  | Replace w/ Answer
If it is changing, what about it needs to change? |  | Replace w/ Answer
#4. Define your buyer persona.
Do you currently have a clearly defined target audience? |  | Replace w/ Answer
Is this audience changing as part of this redesign? |  | Replace w/ Answer
Does your branding and content currently align with that audience? |  | Replace w/ Answer
#5. Protect Optimized Pages.
Research topics that are of interest to your target audience. Align any new content to that persona. |  | Apply 1, 3 or 5
#6. Analyze the competition.
Are there competitor sites that you really like? If so which? Gathering examples in advance will help with the design stage. |  | Replace w/ Answer
What are the top 3 most competitive keywords for your industry |  | Replace w/ Answer
Who are top ranked competitors? |  | Replace w/ Answer
#7. Inventory Your Assets.
What is your most shared or viewed content? |  | Replace w/ Links
What are your most trafficked pages? |  | Replace w/ Links
What are you most ranked pages? |  | Replace w/ Links
Stage II - Plan
#1. As you start planning you may want to ask yourself some of the following questions: |  | Apply 1, 3 or 5
What do I currently like and dislike about my website? |  | Replace w/ Answer
What is missing from the current website? |  | Replace w/ Answer
How does my current site compare to your goals? |  | Replace w/ Answer
What's the first impression I want to give my target audience? |  | Replace w/ Answer
Does my site currently convey a feeling of trustworthyness and authority? |  | Replace w/ Answer
Will this be a whole new website or are the small changes that can be made? |  | Replace w/ Answer
Will the domain name change at all? |  | Replace w/ Answer
What platform do I want my new website to be on? |  | Replace w/ Answer
What is a realistic timeline for this redesign? Define a target date. |  | Replace w/ Answer
What is our budget for this project? |  | Replace w/ Answer
Can we do this work in-house or do we need to hire someone? |  | Replace w/ Answer
#2. As you evaluate platforms you should consider the following: |  | Apply 1, 3 or 5
Name(s) of platform(s) that you are evaluating? |  | Replace w/ Answer
Reputation - Does the platform have a good reputation? |  | Yes or No
Site speed - Does the platform have good deliverabilty - site speed and up-time? |  | Yes or No
SEO friendly - Are things like URLs well structured and search engine friendly? |  | Yes or No
#3. Inventory your assets: |  | Apply 1, 3 or 5
Tip: You may want to track each of these items in a separate spreadsheet.
Use a tool like Screamingfrog.co.uk or Xenus-link-sleuth.en.softonic.com to crawl all the pages of your site and give you an exportable inventory.
Review all website pages and current site architecture. |  | Apply 1, 3 or 5
Note which are your most shared or viewed content? |  | Apply 1, 3 or 5
Evaluate which content is worth keeping. |  | Apply 1, 3 or 5
Did you find duplicate content? |  | Apply 1, 3 or 5
Check pages for 404s and list the most important pages as fixes. |  | Apply 1, 3 or 5
#4. Review your current website architecture: |  | Apply 1, 3 or 5
Plan the new site architecture/structure. |  | Apply 1, 3 or 5
Define which pages will be part of your main and secondary (if there is one) navigation/menu. |  | Apply 1, 3 or 5
Put together a draft outline/sitemap of new website to be designed and built. |  | Apply 1, 3 or 5
#5. Develop a URL mapping document/301 redirect plan: |  | Apply 1, 3 or 5
Tip: This can simply be an excel document noting the old URL and then what the new URL will be. Someone technical will want to apply the 301s later.
It is important to determine which applies to you:
(a) If the site structure has changed (typically then URLs change too). |  | Yes or No
(b) If the site structure has not changed but you want to update URLs to be more SEO and user friendly. |  | Yes or No
Or (c) pages will be merged. |  | Yes or No
#6. Define your content plan: Based on your inventory (exported from step 3 above) |  | Apply 1, 3 or 5
Outline which content stays. |  | Apply 1, 3 or 5
Outline which content goes. |  | Apply 1, 3 or 5
Outline which content needs to be rewritten. |  | Apply 1, 3 or 5
Identify what calls to actions need to be added. |  | Apply 1, 3 or 5
Stage III - Design
#1. Review and sign-off on wireframes of the new layout (usually no more than 2-3 revisions). |  | Apply 1, 3 or 5
#2. Review design prototypes/mock-ups (usually no more than 2-3 revisions). |  | Apply 1, 3 or 5
#3. Finalize color scheme to match branding (optional). #4. Hand over all visual assets (optional). |  | Apply 1, 3 or 5
#4. Hand over all visual assets (optional). |  | Apply 1, 3 or 5
Stage IV - Build
#1. Finalize the new platform. What's the name of the platform that was chosen? (If it applies) |  | Apply 1, 3 or 5
Note: The site should be built on the new platform, if one was chosen. (If it applies)
#2. Finalize all visual and content assets. |  | Apply 1, 3 or 5
#3. Make sure that the staging/development site is set up as no-index. |  | Apply 1, 3 or 5
#4. Finalize all web content at this stage. |  | Apply 1, 3 or 5
#5. Continue to play with the site during this stage, and review overall flow and usability |  | Apply 1, 3 or 5
Stage V - Optimize, Test and Deliver
#1. Optimize content |  | Apply 1, 3 or 5
As part of the optimization process should should check the following:
(a) Is the new site multi browser compatible. Use browsershots.org |  | Apply 1, 3 or 5
(b) Do custom/user friendly 404 pages exist? |  | Apply 1, 3 or 5
(c) Run site through a broken link checker. |  | Apply 1, 3 or 5
(d) Set up and add sitemap.xml and robots.txt files. |  | Apply 1, 3 or 5
(e) Check for common errors like grammar and misspellings. |  | Apply 1, 3 or 5
Shareability
Can users easily subscribe to content? |  | Yes or No
Can users easily share pages, photos, posts etc.? |  | Yes or No
Analytics
Add your favorite and/or previous analytics tool back to the site |  | Apply 1, 3 or 5
Keywords
Typical content pages cover no more than one topic/keyword per page. |  | Apply 1, 3 or 5
Keywords are included within a well thoughtout page title and page descriptions. |  | Apply 1, 3 or 5
Keywords are incorporated naturally throughout content and content is designed to match persona needs and overall value proposition. |  | Apply 1, 3 or 5
Calls to actions/offers focus on the topic specified in a page. |  | Apply 1, 3 or 5
Is there clear and meaningful use of keywords throughout the site? |  | Yes or No
Does the content relate to your target audience? |  | Yes or No
#2. Test site. |  | Apply 1, 3 or 5
Make sure all old pages redirect to proper new pages. |  | Apply 1, 3 or 5
Tip: Pages should be (or have been) redirected on a one-by-one basis not from the root domain.
Check navigation
Is there a clear content hierarchy and organization? |  | Yes or No
Is the site structure intuitive and user friendly? |  | Yes or No
Design & layout
Perform an HTML validation test via a CSS validator like validator.w3.org. |  | Apply 1, 3 or 5
Assess the overall design and layout. Does it meet your expectations? |  | Yes or No
Performance
Do your pages load quickly? Run test with a tool like Yslow - developer.yahoo.com/yslow/ |  | Yes or No
#3. Sign off on site and prepare for launch. |  | Apply 1, 3 or 5
Get sign off from key management. |  | Apply 1, 3 or 5
Determine and set launch date. |  | Apply 1, 3 or 5
Stage VI - Launch & Promote
#1. On actual launch date prepare for things to go wrong. All hands on deck. |  | Apply 1, 3 or 5
#2. Announce new site launch (ideally within 1 week of launch, but not on actual date of launch): |  | Apply 1, 3 or 5
Via email |  | Apply 1, 3 or 5
Via social media |  | Apply 1, 3 or 5
Via PR |  | Apply 1, 3 or 5
Via blog(s) |  | Apply 1, 3 or 5
Other |  | Apply 1, 3 or 5
#3. Create an ongoing content strategy. |  | Apply 1, 3 or 5
Start a blog or continue blogging. If you are already blogging this is a good time to pump up the volume. |  | Apply 1, 3 or 5
#4. Prepare for ongoing maintenance. |  | Apply 1, 3 or 5
Stage VII - Analyze
#1. Within 1 week of redesign run a check to see that your site is indexed (check all major search engines) |  | Apply 1, 3 or 5
How Many pages are indexed? |  | Replace w/ Answer
Are all of your important pages indexed? |  | Replace w/ Answer
#2. Confirm that your Robots.txt file(s) is set up properly. |  | Apply 1, 3 or 5
#3. Resubmit your .XML sitemap(s) via (Google and Bing) webmaster tools about 1 week after launch. |  | Apply 1, 3 or 5
#4. Add a public HTML sitemap (if you haven't already). |  | Apply 1, 3 or 5
#5. Add your favorite and/or previous analytics tool back to the site |  | Apply 1, 3 or 5
#6. Benchmark your metrics at 1, 3 and 6 month markers post redesign. |  | Apply 1, 3 or 5
Number of visits/visitors/unique visitors (monthly average). |  | Enter Stats
Bounce rate (monthly average). |  | Enter Stats
Time on site (monthly average). |  | Enter Stats
Top performing keywords (in terms of rank, traffic and lead generation). |  | Enter Stats
Number of inbound linking domains. |  | Enter Stats
Total number of new leads/form submissions (per month). |  | Enter Stats
Total amount of sales generated (per month). |  | Enter Stats
Total number of total pages indexed. |  | Enter Stats
Total number of pages that receive traffic. |  | Enter Stats
#7. Continue keyword research (this does not stop just because you have a new site). |  | Apply 1, 3 or 5
by