## Sheet1
Selection Task | Status
Selection Team
Select an HRMS selection project lead and a C-Level executive to sponsor your project | 1
Identify key stakeholders(user groups) including operational HR staff, HR management and employees outside of HR | 2
Requirements Gathering with the User Groups
Create a map of current HR processes with cycle-times to identify bottlenecks in efficiency | 3
Identify paper-based HR process and shortcomings of existing HR systems | 4
Identify key operational challenges you aim to solve with the new HRMS System | 5
System Specification
Identify the total number of users who will require system access | 6
Determine preferred delivery platform (cloud, on-premise, hybrid etc.) | 7
Identify mobile access requirements (web-app, native iOS, native Android etc.) | 8
Vendor Services
Document requirements for support scope and delivery method (phone support, online support etc.) | 9
Document requirements for training scope and delivery method (classroom training, on-site training) | 10
Document data migration requirements for critical data and reports | 11
Return on Investment Forecast
Identify preferred payment method (SaaS, perpetual license etc.) | 12
Compute ROI: consider TCO, return calculations, value addition, time & cost savings | 13
Report on ROI forecasts to senior management and seek project approval | 14
Vendor Shortlisting
Identify HRMS vendors who meet your key requirements and send them an RFI document | 15
Compile requirements based on RFI responses and business processes into an RFP document | 16
Narrow shortlist based on RFP responses to produce final shortlist | 17
Vendor Selection
Build selection teams to attend software demo including user group members | 18
Produce an RFQ document and send to all vendors that were demoed including request for 2/3 references | 19
Assemble selection committee to review and finalize the vendor | 20
Proceed to contract negotiations | 21