## rawData
ID | State | cycle time | Start Date | End Date | Story Points
43497 | Done | 14 | 2013-01-03 | 2013-01-17 | 8
43771 | Done | 163 | 2012-07-25 | 2013-01-04 | 2
46942 | Done | 0 | 2012-12-03 | 2012-12-03 | 3
48942 | Done | 8 | 2012-11-22 | 2012-11-30 | 8
48997 | Done | 11 | 2012-11-22 | 2012-12-03 | 8
49356 | Done | 11 | 2012-11-22 | 2012-12-03 | 13
49643 | Done | 5 | 2012-11-28 | 2012-12-03 | 2
48461 | Done | 11 | 2012-11-23 | 2012-12-04 | 5
48508 | Done | 11 | 2012-11-23 | 2012-12-04 | 8
47761 | Done | 15 | 2012-11-22 | 2012-12-07 | 13
47761 | Done | 2 | 2012-12-05 | 2012-12-07 | 13
49449 | Done | 2 | 2012-12-05 | 2012-12-07 | 3
48945 | Done | 22 | 2012-11-21 | 2012-12-13 | 8
48945 | Done | 9 | 2012-12-04 | 2012-12-13 | 8
49334 | Done | 7 | 2012-12-06 | 2012-12-13 | 8
48558 | Done | 8 | 2012-11-26 | 2012-12-04 | 5
48567 | Done | 9 | 2012-12-04 | 2012-12-13 | 5
48568 | Done | 7 | 2012-12-06 | 2012-12-13 | 3
48569 | Done | 6 | 2012-11-28 | 2012-12-04 | 3
48570 | Done | 12 | 2012-11-22 | 2012-12-04 | 5
48571 | Done | 8 | 2012-12-05 | 2012-12-13 | 3
49288 | Done | 10 | 2012-12-04 | 2012-12-14 | 2
48944 | Done | 12 | 2012-12-05 | 2012-12-17 | 8
49331 | Done | 19 | 2012-11-29 | 2012-12-18 | 13
48999 | Done | 13 | 2012-12-05 | 2012-12-18 | 8
49006 | Done | 13 | 2012-12-05 | 2012-12-18 | 5
49331 | Done | 13 | 2012-12-05 | 2012-12-18 | 13
49647 | Done | 11 | 2012-12-07 | 2012-12-18 | 8
49751 | Done | 31 | 2012-12-07 | 2013-01-07 | 8
49776 | Done | 26 | 2012-12-12 | 2013-01-07 | 5
49751 | Done | 5 | 2013-01-02 | 2013-01-07 | 8
49776 | Done | 4 | 2013-01-03 | 2013-01-07 | 5
48466 | Done | 24 | 2012-12-17 | 2013-01-10 | 8
48466 | Done | 7 | 2013-01-03 | 2013-01-10 | 8
49000 | Done | 11 | 2013-01-03 | 2013-01-14 | 5
49333 | Done | 11 | 2013-01-03 | 2013-01-14 | 8
49015 | Done | 12 | 2013-01-03 | 2013-01-15 | 8
49649 | Done | 8 | 2013-01-09 | 2013-01-17 | 5
49649 | Done | 0 | 2013-01-17 | 2013-01-17 | 5
47814 | Done | 38 | 2012-12-14 | 2013-01-21 | 5
47814 | Done | 18 | 2013-01-03 | 2013-01-21 | 5
49054 | Done | 9 | 2013-01-07 | 2013-01-16 | 3
49055 | Done | 9 | 2013-01-07 | 2013-01-16 | 5
49065 | Done | 6 | 2013-01-11 | 2013-01-17 | 5
49066 | Done | 10 | 2013-01-07 | 2013-01-17 | 5
49069 | Done | 0 | 2013-01-07 | 2013-01-07 | 1
49072 | Done | 41 | 2012-12-05 | 2013-01-15 | 5
49072 | Done | 13 | 2013-01-02 | 2013-01-15 | 5
49088 | Done | 12 | 2012-11-23 | 2012-12-05 | 5
49114 | Done | 12 | 2012-11-22 | 2012-12-04 | 8
49173 | Done | 11 | 2013-01-03 | 2013-01-14 | 8
47814 | Done | 4 | 2013-01-17 | 2013-01-21 | 5
47726 | Done | 40 | 2012-12-13 | 2013-01-22 | 8
49289 | Done | 10 | 2012-12-03 | 2012-12-13 | 5
47726 | Done | 19 | 2013-01-03 | 2013-01-22 | 8
50262 | Done | 13 | 2013-01-09 | 2013-01-22 | 8
50262 | Done | 6 | 2013-01-16 | 2013-01-22 | 8
47726 | Done | 5 | 2013-01-17 | 2013-01-22 | 8
50331 | Done | 7 | 2013-01-17 | 2013-01-24 | 3
50431 | Done | 7 | 2013-01-18 | 2013-01-25 | 5
50144 | Done | 4 | 2013-01-21 | 2013-01-25 | 5
50862 | Done | 4 | 2013-01-21 | 2013-01-25 | 2
49357 | Done | 35 | 2012-11-16 | 2012-12-21
49357 | Done | 25 | 2012-11-26 | 2012-12-21
49357 | Done | 9 | 2012-12-12 | 2012-12-21
49386 | Done | 9 | 2012-11-20 | 2012-11-29
49386 | Done | 7 | 2012-11-22 | 2012-11-29
49394 | Done | 5 | 2012-11-30 | 2012-12-05 | 5
49397 | Done | 34 | 2012-12-13 | 2013-01-16 | 1
50109 | Done | 25 | 2013-01-04 | 2013-01-29 | 5
49458 | Done | 40 | 2012-11-21 | 2012-12-31
49529 | Done | 20 | 2012-11-22 | 2012-12-12
49529 | Done | 1 | 2012-12-11 | 2012-12-12
49588 | Done | 0 | 2012-11-26 | 2012-11-26
49590 | Done | 2 | 2012-11-26 | 2012-11-28
49595 | Done | 16 | 2012-12-11 | 2012-12-27
49595 | Done | 15 | 2012-12-12 | 2012-12-27
49595 | Done | 6 | 2012-12-21 | 2012-12-27
49617 | Done | 44 | 2012-11-27 | 2013-01-10
49617 | Done | 35 | 2012-12-06 | 2013-01-10
49617 | Done | 17 | 2012-12-24 | 2013-01-10
49626 | Done | 6 | 2012-11-27 | 2012-12-03
50109 | Done | 13 | 2013-01-16 | 2013-01-29 | 5
50392 | Done | 5 | 2013-01-24 | 2013-01-29 | 8
48962 | Done | 21 | 2013-01-09 | 2013-01-30 | 40
48962 | Done | 13 | 2013-01-17 | 2013-01-30 | 40
51008 | Done | 0 | 2013-02-01 | 2013-02-01 | 0
49774 | Done | 14 | 2013-01-22 | 2013-02-05 | 5
49774 | Done | 6 | 2013-01-30 | 2013-02-05 | 5
49003 | Done | 6 | 2013-01-31 | 2013-02-06 | 3
49002 | Done | 13 | 2013-01-25 | 2013-02-07 | 3
49711 | Done | 0 | 2012-12-19 | 2012-12-19 | 5
49748 | Done | 8 | 2012-12-03 | 2012-12-11
49748 | Done | 4 | 2012-12-07 | 2012-12-11
49002 | Done | 8 | 2013-01-30 | 2013-02-07 | 3
49004 | Done | 6 | 2013-02-01 | 2013-02-07 | 3
49754 | Done | 43 | 2012-12-04 | 2013-01-16
48943 | Done | 9 | 2013-01-31 | 2013-02-09 | 13
50406 | Done | 11 | 2013-01-31 | 2013-02-11 | 8
49286 | Done | 12 | 2013-01-31 | 2013-02-12 | 5
49328 | Done | 12 | 2013-01-31 | 2013-02-12 | 5
49790 | Done | 40 | 2012-12-06 | 2013-01-15 | 5
49790 | Done | 13 | 2013-01-02 | 2013-01-15 | 5
49791 | Done | 36 | 2012-12-10 | 2013-01-15 | 1
49791 | Done | 13 | 2013-01-02 | 2013-01-15 | 1
49894 | Done | 39 | 2012-12-06 | 2013-01-14
49909 | Done | 23 | 2012-12-17 | 2013-01-09
49917 | Done | 4 | 2012-12-07 | 2012-12-11
50004 | Deleted | 36 | 2012-12-11 | 2013-01-16
50008 | Done | 0 | 2012-12-11 | 2012-12-11
50022 | Done | 36 | 2012-12-11 | 2013-01-16
50031 | Done | 0 | 2012-12-11 | 2012-12-11
50041 | Done | 36 | 2012-12-11 | 2013-01-16
50048 | Done | 35 | 2012-12-12 | 2013-01-16
50048 | Done | 26 | 2012-12-21 | 2013-01-16
50048 | Done | 6 | 2013-01-10 | 2013-01-16
50053 | Done | 9 | 2012-12-12 | 2012-12-21
50061 | Done | 8 | 2012-12-12 | 2012-12-20
50061 | Done | -14 | 2013-01-03 | 2012-12-20
50067 | Done | 28 | 2012-12-12 | 2013-01-09
50097 | Deleted | 1 | 2013-01-07 | 2013-01-08 | 5
50099 | Done | 27 | 2012-12-13 | 2013-01-09
48960 | Done | 14 | 2013-01-30 | 2013-02-13 | 8
49001 | Done | 2 | 2013-02-11 | 2013-02-13 | 3
50139 | Done | 33 | 2012-12-14 | 2013-01-16
50139 | Done | 16 | 2012-12-31 | 2013-01-16
48960 | Done | 0 | 2013-02-13 | 2013-02-13 | 8
50157 | Done | 13 | 2012-12-18 | 2012-12-31
50190 | Done | 28 | 2012-12-21 | 2013-01-18
50190 | Done | 8 | 2013-01-10 | 2013-01-18
50195 | Done | 24 | 2012-12-21 | 2013-01-14
50195 | Done | 4 | 2013-01-10 | 2013-01-14
50204 | Done | 26 | 2012-12-21 | 2013-01-16
50204 | Done | 0 | 2013-01-16 | 2013-01-16
50213 | Done | 0 | 2012-12-26 | 2012-12-26
50216 | Done | 22 | 2012-12-27 | 2013-01-18
50216 | Done | 15 | 2013-01-03 | 2013-01-18
50221 | Done | 20 | 2012-12-27 | 2013-01-16
50230 | Done | 0 | 2012-12-28 | 2012-12-28
50234 | Done | 0 | 2012-12-31 | 2012-12-31
50239 | Done | 0 | 2012-12-31 | 2012-12-31
50247 | Done | 14 | 2013-01-02 | 2013-01-16
50259 | Done | 11 | 2013-01-03 | 2013-01-14 | 5
50260 | Done | 22 | 2013-01-03 | 2013-01-25 | 2
50260 | Done | 4 | 2013-01-21 | 2013-01-25 | 2
50261 | Done | 12 | 2013-01-03 | 2013-01-15 | 5
49005 | Done | 1 | 2013-02-14 | 2013-02-15 | 3
49653 | Done | 75 | 2012-12-05 | 2013-02-18 | 20
50298 | Done | 12 | 2013-01-03 | 2013-01-15 | 2
50300 | Done | 6 | 2013-01-09 | 2013-01-15 | 2
50302 | Done | 6 | 2013-01-09 | 2013-01-15 | 2
50304 | Done | 12 | 2013-01-03 | 2013-01-15 | 3
50309 | Done | 4 | 2013-01-07 | 2013-01-11 | 5
50312 | Done | 13 | 2013-01-03 | 2013-01-16
50322 | In Progress | 5 | 2013-01-03 | 2013-01-08
50322 | In Progress | -17 | 2013-01-25 | 2013-01-08
50322 | In Progress | -22 | 2013-01-30 | 2013-01-08
50322 | In Progress | -36 | 2013-02-13 | 2013-01-08
49653 | Done | 19 | 2013-01-30 | 2013-02-18 | 20
50355 | Done | 10 | 2013-01-04 | 2013-01-14
49335 | Done | 18 | 2013-01-31 | 2013-02-18 | 20
50399 | Done | 0 | 2013-01-07 | 2013-01-07
50401 | Deleted | 9 | 2013-01-07 | 2013-01-16
50401 | Deleted | 5 | 2013-01-11 | 2013-01-16
50402 | In Progress | 9 | 2013-01-07 | 2013-01-16
50402 | In Progress | -27 | 2013-02-12 | 2013-01-16
49335 | Done | 5 | 2013-02-13 | 2013-02-18 | 20
50415 | Deleted | 0 | 2013-01-08 | 2013-01-08
50418 | Done | 8 | 2013-01-08 | 2013-01-16
50427 | Done | 0 | 2013-01-08 | 2013-01-08
49653 | Done | 5 | 2013-02-13 | 2013-02-18 | 20
50471 | Done | 0 | 2013-01-09 | 2013-01-09
50510 | Done | 3 | 2013-01-11 | 2013-01-14 | 5
50579 | In Progress | 6 | 2013-01-10 | 2013-01-16
50579 | In Progress | -33 | 2013-02-18 | 2013-01-16
50659 | Done | 0 | 2013-01-11 | 2013-01-11
50662 | Done | 5 | 2013-01-11 | 2013-01-16
50665 | Done | 5 | 2013-01-11 | 2013-01-16
50688 | Done | 0 | 2013-01-11 | 2013-01-11 | 2
50694 | Done | 6 | 2013-01-11 | 2013-01-17 | 3
49654 | Done | 19 | 2013-02-01 | 2013-02-20 | 20
50722 | Done | 0 | 2013-01-14 | 2013-01-14
50731 | Done | 2 | 2013-01-14 | 2013-01-16 | 3
50755 | Done | 12 | 2013-01-17 | 2013-01-29 | 8
50756 | Done | 8 | 2013-02-04 | 2013-02-12 | 8
50818 | Done | 2 | 2013-01-16 | 2013-01-18
50823 | Done | 0 | 2013-01-16 | 2013-01-16
50835 | Done | 6 | 2013-01-23 | 2013-01-29 | 3
50836 | Done | 6 | 2013-01-17 | 2013-01-23 | 2
50837 | Done | 12 | 2013-01-17 | 2013-01-29 | 3
49654 | Done | 7 | 2013-02-13 | 2013-02-20 | 20
50863 | Done | 8 | 2013-01-21 | 2013-01-29 | 3
50864 | Done | 8 | 2013-01-21 | 2013-01-29 | 5
50865 | Done | 7 | 2013-01-21 | 2013-01-28 | 8
50979 | Done | 0 | 2013-01-17 | 2013-01-17
50983 | Done | 0 | 2013-01-17 | 2013-01-17
50985 | Done | 0 | 2013-01-17 | 2013-01-17
50999 | Done | 0 | 2013-01-18 | 2013-01-18
50712 | Done | 7 | 2013-02-14 | 2013-02-21 | 5
51036 | Done | 9 | 2013-01-23 | 2013-02-01
51041 | Done | 0 | 2013-02-11 | 2013-02-11
51042 | Done | 19 | 2013-02-01 | 2013-02-20
51042 | Done | 7 | 2013-02-13 | 2013-02-20
51046 | Done | 1 | 2013-01-23 | 2013-01-24
51047 | Done | 1 | 2013-01-23 | 2013-01-24
51050 | Done | 3 | 2013-02-08 | 2013-02-11
51051 | In Progress | 9 | 2013-01-23 | 2013-02-01
51051 | In Progress | -12 | 2013-02-13 | 2013-02-01
51054 | Done | 0 | 2013-02-04 | 2013-02-04
51055 | Done | 2 | 2013-02-11 | 2013-02-13
51057 | Done | 0 | 2013-02-04 | 2013-02-04
51059 | Done | 0 | 2013-02-04 | 2013-02-04
51061 | Done | 14 | 2013-02-06 | 2013-02-20
51062 | Done | 21 | 2013-01-23 | 2013-02-13
51064 | Done | 24 | 2013-01-28 | 2013-02-21
51068 | Done | 12 | 2013-01-23 | 2013-02-04
51069 | Done | 6 | 2013-01-29 | 2013-02-04
51072 | Done | 10 | 2013-01-28 | 2013-02-07
51072 | Done | 0 | 2013-02-07 | 2013-02-07
51119 | Done | 27 | 2013-01-23 | 2013-02-19
51119 | Done | 13 | 2013-02-06 | 2013-02-19
51119 | Done | 6 | 2013-02-13 | 2013-02-19
51174 | Done | 3 | 2013-02-05 | 2013-02-08 | 5
51175 | Done | 15 | 2013-02-06 | 2013-02-21
51178 | Done | 14 | 2013-02-06 | 2013-02-20
51184 | Done | 3 | 2013-02-05 | 2013-02-08 | 5
51199 | Done | 11 | 2013-02-01 | 2013-02-12 | 5
51212 | Done | 8 | 2013-02-04 | 2013-02-12 | 3
51239 | Done | 0 | 2013-02-05 | 2013-02-05 | 1
51272 | Done | 2 | 2013-02-11 | 2013-02-13
51274 | Done | 0 | 2013-02-04 | 2013-02-04
51276 | Done | 4 | 2013-01-31 | 2013-02-04
51277 | Done | 0 | 2013-02-14 | 2013-02-14
51278 | Done | 2 | 2013-02-19 | 2013-02-21
51280 | Done | 0 | 2013-02-20 | 2013-02-20
51308 | Done | 6 | 2013-02-05 | 2013-02-11 | 5
51309 | Done | 6 | 2013-01-30 | 2013-02-05
51311 | Done | 21 | 2013-01-30 | 2013-02-20
51312 | Done | 15 | 2013-02-06 | 2013-02-21
51313 | Done | 12 | 2013-02-08 | 2013-02-20
51470 | Done | 0 | 2013-02-07 | 2013-02-07
51609 | Done | 3 | 2013-02-01 | 2013-02-04 | 1
51611 | Done | 4 | 2013-02-01 | 2013-02-05 | 1
51613 | Done | 4 | 2013-02-01 | 2013-02-05 | 2
51694 | Deleted | 2 | 2013-02-06 | 2013-02-08
51801 | Done | 5 | 2013-02-08 | 2013-02-13
51851 | Done | 6 | 2013-02-15 | 2013-02-21
52053 | Done | 6 | 2013-02-14 | 2013-02-20 | 1

## correlation
Returns the correlation coefficient of the array1 and array2 cell ranges. Use the correlation coefficient to determine the relationship between two properties. For example, you can examine the relationship between a location's average temperature and the use of air conditioners.
The Pearson correlation is +1 in the case of a perfect direct (increasing) linear relationship (correlation), −1 in the case of a perfect decreasing (inverse) linear relationship (anticorrelation),[5] and some value between −1 and 1 in all other cases, indicating the degree of linear dependence between the variables. As it approaches zero there is less of a relationship (closer to uncorrelated). The closer the coefficient is to either −1 or 1, the stronger the correlation between the variables.
ID | cycle time | Story Points
49288 | 10 | 2
49643 | 5 | 2
50862 | 4 | 2 | Correlation | 0.24605
49001 | 2 | 3
49002 | 13 | 3
49002 | 8 | 3
49003 | 6 | 3
49004 | 6 | 3
49005 | 1 | 3
49449 | 2 | 3
50331 | 7 | 3
47814 | 38 | 5
47814 | 18 | 5
47814 | 4 | 5
48461 | 11 | 5
49000 | 11 | 5
49006 | 13 | 5
49286 | 12 | 5
49328 | 12 | 5
49649 | 8 | 5
49774 | 14 | 5
49774 | 6 | 5
49776 | 26 | 5
49776 | 4 | 5
50109 | 25 | 5
50109 | 13 | 5
50144 | 4 | 5
50431 | 7 | 5
50712 | 7 | 5
47726 | 40 | 8
47726 | 19 | 8
47726 | 5 | 8
48466 | 24 | 8
48466 | 7 | 8
48508 | 11 | 8
48942 | 8 | 8
48944 | 12 | 8
48945 | 22 | 8
48945 | 9 | 8
48960 | 14 | 8
48997 | 11 | 8
48999 | 13 | 8
49015 | 12 | 8
49333 | 11 | 8
49334 | 7 | 8
49647 | 11 | 8
49751 | 31 | 8
49751 | 5 | 8
50262 | 13 | 8
50262 | 6 | 8
50392 | 5 | 8
50406 | 11 | 8
47761 | 15 | 13
47761 | 2 | 13
48943 | 9 | 13
49331 | 19 | 13
49331 | 13 | 13
49356 | 11 | 13
49335 | 18 | 20
49335 | 5 | 20
49653 | 75 | 20
49653 | 19 | 20
49653 | 5 | 20
49654 | 19 | 20
49654 | 7 | 20
48962 | 21 | 40
48962 | 13 | 40

## Charts
67 Work Items

## Data
ID | State | cycle time | Start Date | End Date | Story Points | Velocity | Throughput | Iteration | Start | End | Average velocity | 88
48942 | Done | 8 | 2012-11-22 | 2012-11-30 | 8 | 44 | 6 | 1 | 2012-11-21 | 2012-12-04 | Average Throughput | 10
48997 | Done | 11 | 2012-11-22 | 2012-12-03 | 8 | 110 | 13 | 2 | 2012-12-05 | 2012-12-18 | Total Story Points | 615
49356 | Done | 11 | 2012-11-22 | 2012-12-03 | 13 | 0 | 0 | 3 | 2012-12-19 | 2013-01-01 | Count of work items | 70
49643 | Done | 5 | 2012-11-28 | 2012-12-03 | 2 | 63 | 9 | 4 | 2013-01-02 | 2013-01-15
48461 | Done | 11 | 2012-11-23 | 2012-12-04 | 5 | 98 | 17 | 5 | 2013-01-16 | 2013-01-29
48508 | Done | 11 | 2012-11-23 | 2012-12-04 | 8 | 133 | 13 | 6 | 2013-01-30 | 2013-02-12
47761 | Done | 15 | 2012-11-22 | 2012-12-07 | 13 | 167 | 12 | 7 | 2013-02-13 | 2013-02-26
47761 | Done | 2 | 2012-12-05 | 2012-12-07 | 13 | 0 | 0 | 8 | 2013-02-27 | 2013-03-12
49449 | Done | 2 | 2012-12-05 | 2012-12-07 | 3 | 0 | 0 | 9 | 2013-03-13 | 2013-03-26
48945 | Done | 22 | 2012-11-21 | 2012-12-13 | 8 | 0 | 0 | 10 | 2013-03-27 | 2013-04-09
48945 | Done | 9 | 2012-12-04 | 2012-12-13 | 8 |  |  | 11 | 2013-04-10 | 2013-04-23
49334 | Done | 7 | 2012-12-06 | 2012-12-13 | 8 |  |  | 12 | 2013-04-24 | 2013-05-07 | When are we going to be done?
49288 | Done | 10 | 2012-12-04 | 2012-12-14 | 2 |  |  | 13 | 2013-05-08 | 2013-05-21 | Using average velocity | 6.9886
48944 | Done | 12 | 2012-12-05 | 2012-12-17 | 8 |  |  | 14 | 2013-05-22 | 2013-06-04 | Using average throughput | 7
49331 | Done | 19 | 2012-11-29 | 2012-12-18 | 13 |  |  | 15 | 2013-06-05 | 2013-06-18
48999 | Done | 13 | 2012-12-05 | 2012-12-18 | 8 |  |  | 16 | 2013-06-19 | 2013-07-02
49006 | Done | 13 | 2012-12-05 | 2012-12-18 | 5 |  |  | 17 | 2013-07-03 | 2013-07-16
49331 | Done | 13 | 2012-12-05 | 2012-12-18 | 13 |  |  | 18 | 2013-07-17 | 2013-07-30
49647 | Done | 11 | 2012-12-07 | 2012-12-18 | 8 |  |  | 19 | 2013-07-31 | 2013-08-13
49751 | Done | 31 | 2012-12-07 | 2013-01-07 | 8 |  |  | 20 | 2013-08-14 | 2013-08-27
49776 | Done | 26 | 2012-12-12 | 2013-01-07 | 5 |  |  | 21 | 2013-08-28 | 2013-09-10
49751 | Done | 5 | 2013-01-02 | 2013-01-07 | 8 |  |  | 22 | 2013-09-11 | 2013-09-24
49776 | Done | 4 | 2013-01-03 | 2013-01-07 | 5 |  |  | 23 | 2013-09-25 | 2013-10-08 | 95% | 28.75
48466 | Done | 24 | 2012-12-17 | 2013-01-10 | 8 |  |  | 24 | 2013-10-09 | 2013-10-22 | 75% | 13.75
48466 | Done | 7 | 2013-01-03 | 2013-01-10 | 8 |  |  | 25 | 2013-10-23 | 2013-11-05 | 50% | 11
49000 | Done | 11 | 2013-01-03 | 2013-01-14 | 5 |  |  | 26 | 2013-11-06 | 2013-11-19 | 25% | 6
49333 | Done | 11 | 2013-01-03 | 2013-01-14 | 8 |  |  | 27 | 2013-11-20 | 2013-12-03 | Average | 12.2143
49015 | Done | 12 | 2013-01-03 | 2013-01-15 | 8 |  |  | 28 | 2013-12-04 | 2013-12-17
49649 | Done | 8 | 2013-01-09 | 2013-01-17 | 5 |  |  | 29 | 2013-12-18 | 2013-12-31
49649 | Done | 0 | 2013-01-17 | 2013-01-17 | 5 |  |  | 30 | 2014-01-01 | 2014-01-14
47814 | Done | 38 | 2012-12-14 | 2013-01-21 | 5
47814 | Done | 18 | 2013-01-03 | 2013-01-21 | 5
47814 | Done | 4 | 2013-01-17 | 2013-01-21 | 5
47726 | Done | 40 | 2012-12-13 | 2013-01-22 | 8
47726 | Done | 19 | 2013-01-03 | 2013-01-22 | 8
50262 | Done | 13 | 2013-01-09 | 2013-01-22 | 8
50262 | Done | 6 | 2013-01-16 | 2013-01-22 | 8
47726 | Done | 5 | 2013-01-17 | 2013-01-22 | 8
50331 | Done | 7 | 2013-01-17 | 2013-01-24 | 3
50431 | Done | 7 | 2013-01-18 | 2013-01-25 | 5
50144 | Done | 4 | 2013-01-21 | 2013-01-25 | 5
50862 | Done | 4 | 2013-01-21 | 2013-01-25 | 2
50109 | Done | 25 | 2013-01-04 | 2013-01-29 | 5
50109 | Done | 13 | 2013-01-16 | 2013-01-29 | 5
50392 | Done | 5 | 2013-01-24 | 2013-01-29 | 8
48962 | Done | 21 | 2013-01-09 | 2013-01-30 | 40
48962 | Done | 13 | 2013-01-17 | 2013-01-30 | 40
51008 | Done | 0 | 2013-02-01 | 2013-02-01 | 0
49774 | Done | 14 | 2013-01-22 | 2013-02-05 | 5
49774 | Done | 6 | 2013-01-30 | 2013-02-05 | 5
49003 | Done | 6 | 2013-01-31 | 2013-02-06 | 3
49002 | Done | 13 | 2013-01-25 | 2013-02-07 | 3
49002 | Done | 8 | 2013-01-30 | 2013-02-07 | 3
49004 | Done | 6 | 2013-02-01 | 2013-02-07 | 3
48943 | Done | 9 | 2013-01-31 | 2013-02-09 | 13
50406 | Done | 11 | 2013-01-31 | 2013-02-11 | 8
49286 | Done | 12 | 2013-01-31 | 2013-02-12 | 5
49328 | Done | 12 | 2013-01-31 | 2013-02-12 | 5
48960 | Done | 14 | 2013-01-30 | 2013-02-13 | 8
49001 | Done | 2 | 2013-02-11 | 2013-02-13 | 3
48960 | Done | 0 | 2013-02-13 | 2013-02-13 | 8
49005 | Done | 1 | 2013-02-14 | 2013-02-15 | 3
49653 | Done | 75 | 2012-12-05 | 2013-02-18 | 20
49653 | Done | 19 | 2013-01-30 | 2013-02-18 | 20
49335 | Done | 18 | 2013-01-31 | 2013-02-18 | 20
49335 | Done | 5 | 2013-02-13 | 2013-02-18 | 20
49653 | Done | 5 | 2013-02-13 | 2013-02-18 | 20
49654 | Done | 19 | 2013-02-01 | 2013-02-20 | 20
49654 | Done | 7 | 2013-02-13 | 2013-02-20 | 20
50712 | Done | 7 | 2013-02-14 | 2013-02-21 | 5

## size-Time Correlation
ID | State | cycle time | Start Date | End Date | Story Points
48942 | Done | 8 | 2012-11-22 | 2012-11-30 | 8 | Earliest start | 2012-11-21
48997 | Done | 11 | 2012-11-22 | 2012-12-03 | 8 | Lates finish | 2013-02-21
49356 | Done | 11 | 2012-11-22 | 2012-12-03 | 13
49643 | Done | 5 | 2012-11-28 | 2012-12-03 | 2
48461 | Done | 11 | 2012-11-23 | 2012-12-04 | 5
48508 | Done | 11 | 2012-11-23 | 2012-12-04 | 8
47761 | Done | 15 | 2012-11-22 | 2012-12-07 | 13
47761 | Done | 2 | 2012-12-05 | 2012-12-07 | 13
49449 | Done | 2 | 2012-12-05 | 2012-12-07 | 3
48945 | Done | 22 | 2012-11-21 | 2012-12-13 | 8
48945 | Done | 9 | 2012-12-04 | 2012-12-13 | 8
49334 | Done | 7 | 2012-12-06 | 2012-12-13 | 8
49288 | Done | 10 | 2012-12-04 | 2012-12-14 | 2
48944 | Done | 12 | 2012-12-05 | 2012-12-17 | 8
49331 | Done | 19 | 2012-11-29 | 2012-12-18 | 13
48999 | Done | 13 | 2012-12-05 | 2012-12-18 | 8
49006 | Done | 13 | 2012-12-05 | 2012-12-18 | 5
49331 | Done | 13 | 2012-12-05 | 2012-12-18 | 13
49647 | Done | 11 | 2012-12-07 | 2012-12-18 | 8
49751 | Done | 31 | 2012-12-07 | 2013-01-07 | 8
49776 | Done | 26 | 2012-12-12 | 2013-01-07 | 5
49751 | Done | 5 | 2013-01-02 | 2013-01-07 | 8
49776 | Done | 4 | 2013-01-03 | 2013-01-07 | 5
48466 | Done | 24 | 2012-12-17 | 2013-01-10 | 8
48466 | Done | 7 | 2013-01-03 | 2013-01-10 | 8
49000 | Done | 11 | 2013-01-03 | 2013-01-14 | 5
49333 | Done | 11 | 2013-01-03 | 2013-01-14 | 8
49015 | Done | 12 | 2013-01-03 | 2013-01-15 | 8
49649 | Done | 8 | 2013-01-09 | 2013-01-17 | 5
49649 | Done | 0 | 2013-01-17 | 2013-01-17 | 5
47814 | Done | 38 | 2012-12-14 | 2013-01-21 | 5
47814 | Done | 18 | 2013-01-03 | 2013-01-21 | 5
47814 | Done | 4 | 2013-01-17 | 2013-01-21 | 5
47726 | Done | 40 | 2012-12-13 | 2013-01-22 | 8
47726 | Done | 19 | 2013-01-03 | 2013-01-22 | 8
50262 | Done | 13 | 2013-01-09 | 2013-01-22 | 8
50262 | Done | 6 | 2013-01-16 | 2013-01-22 | 8
47726 | Done | 5 | 2013-01-17 | 2013-01-22 | 8
50331 | Done | 7 | 2013-01-17 | 2013-01-24 | 3
50431 | Done | 7 | 2013-01-18 | 2013-01-25 | 5
50144 | Done | 4 | 2013-01-21 | 2013-01-25 | 5
50862 | Done | 4 | 2013-01-21 | 2013-01-25 | 2
50109 | Done | 25 | 2013-01-04 | 2013-01-29 | 5
50109 | Done | 13 | 2013-01-16 | 2013-01-29 | 5
50392 | Done | 5 | 2013-01-24 | 2013-01-29 | 8
48962 | Done | 21 | 2013-01-09 | 2013-01-30 | 40
48962 | Done | 13 | 2013-01-17 | 2013-01-30 | 40
51008 | Done | 0 | 2013-02-01 | 2013-02-01 | 0
49774 | Done | 14 | 2013-01-22 | 2013-02-05 | 5
49774 | Done | 6 | 2013-01-30 | 2013-02-05 | 5
49003 | Done | 6 | 2013-01-31 | 2013-02-06 | 3
49002 | Done | 13 | 2013-01-25 | 2013-02-07 | 3
49002 | Done | 8 | 2013-01-30 | 2013-02-07 | 3
49004 | Done | 6 | 2013-02-01 | 2013-02-07 | 3
48943 | Done | 9 | 2013-01-31 | 2013-02-09 | 13
50406 | Done | 11 | 2013-01-31 | 2013-02-11 | 8
49286 | Done | 12 | 2013-01-31 | 2013-02-12 | 5
49328 | Done | 12 | 2013-01-31 | 2013-02-12 | 5
48960 | Done | 14 | 2013-01-30 | 2013-02-13 | 8
49001 | Done | 2 | 2013-02-11 | 2013-02-13 | 3
48960 | Done | 0 | 2013-02-13 | 2013-02-13 | 8
49005 | Done | 1 | 2013-02-14 | 2013-02-15 | 3
49653 | Done | 75 | 2012-12-05 | 2013-02-18 | 20
49653 | Done | 19 | 2013-01-30 | 2013-02-18 | 20
49335 | Done | 18 | 2013-01-31 | 2013-02-18 | 20
49335 | Done | 5 | 2013-02-13 | 2013-02-18 | 20
49653 | Done | 5 | 2013-02-13 | 2013-02-18 | 20
49654 | Done | 19 | 2013-02-01 | 2013-02-20 | 20
49654 | Done | 7 | 2013-02-13 | 2013-02-20 | 20
50712 | Done | 7 | 2013-02-14 | 2013-02-21 | 5