## RACI Form
RACI Chart
| Process/Project Name |  | Marlton Rotary
| Description of Process |  | Management of projects for Marlton Rotary during July 2018-June 2019 year
| Team Creating RACI |  | Joan, Cynthia, Michael, Fiona, Paul, Marci, Harold, Tim, Bob, Anna Marie, Evans
| RACI Implementation Date |  | 2018-07-24
| Projects | Month | Joan | Cynthia | Bonnie | Chuck | Michael | Fiona | Paul | Bruce | Marci | Evans | Tim | Bob | Anna Marie | Nick
1 | Food drive at Rastellis for Wiley | August/September |  |  |  | R |  |  | C |  |  | C
2 | Invocations | July 18 - June 19 | [6 empty] | R
3 | Unforgotten Haven Clothing Drive | 2018-08-01 | R | C | [7 empty] | C
4 | Firehouse Dinner | 2018-09-11 | [8 empty] | C |  |  |  | R
5 | Military Appreciation Day | 2018-09-15 | A | C | R | I | I |  |  |  |  | I
6 | Poker Game | 2018-09-29 | A | C |  |  | R | [5 empty] | C | C
7 | Harvest Fest | 2018-09-29 | R | [8 empty] | I
8 | PBJ Sandwiches Unforgotten Haven | 2018-10-19 | I | C |  |  |  | R |  |  | C | C
9 | Chipotle Fundraiser | Fall |  |  |  | R
10 | Dictionaries | Fall | [7 empty] | R |  |  | I | I
11 | MBA Luncheon | 2018-11-14 |  |  |  |  | R |  |  |  | C
12 | Cathedral Kitchen | 2018-12-03 | C | [10 empty] | R
13 | Library Display | December | R
14 | Christmas Party | 2018-12-11 | R
15 | Pack meals at Manna | ? | I |  | I |  |  | R |  |  |  | I
16 | Pancake Breakfast | February or March | A |  | C |  |  |  |  | R |  | I
17 | Shelter Box | ? | A | [7 empty] | R
18 | Police Black Run Preserve 5K | Spring | A | [8 empty] | I |  |  |  | R
19 | Allora fundraiser | Spring | [10 empty] | R
20 | Evesham Maintenance Worker Breakfast | 2019-05-01 | [8 empty] | R | I
21 | Cherokee Scholarships | 2019-05-01 | [8 empty] | A |  |  |  | R
22 | RYLA student award | ? | [12 empty] | R
23 | The Oaks Donation Organization | Twice a year | R | C | [7 empty] | C
24
25
26
27
28
29
30
Steps in buiding the RACI
1 | Identify the positions or functions involved in the process or project and use the title as a label for the column. If you need to capture more positions, add additional columns to your RACI.
2 | List the major steps in your process/project in column B. If you need to capture more than 10 steps, add rows to accomdate.
3 | For each step, identify who is "R" - responsible for that portion of the project or process. There is one and only one "R" for each row.
4 | Where major decisions must be made, add an "A" for the person who is accountable for the decision. There can be only one A in rows that have an "A". Only use an "A" for major decision points in your project or process
5 | Add in where people need to be "C" Consulted or "I" merely Informed of this process step.