## Guidelines
Tab | Purpose
Guidelines | This worksheet. The purpose of this worksheet is to provide general guidance on the content of each worksheet in this template. The Implementation Manager is the owner of this document and is responsible for ensuring that all worksheets are completed in full.
Change Info | This worksheet provides basic information about the change i.e. which project, which service etc. In addition, all ITSM/ITIL change records associated with the implementation should be recorded in this tab. The records entered here are available for selection in the Imp Runbook tab and the Backout Runbook tabs.
Contacts | The contact information for all members of the Implementation team and members of the Command & Control group should be entered here. Information about the implementation team members (role, team, initials etc) is used in the Roster, Imp Runbook and Backout Runbook tabs.
Roster | This worksheet lets the Imp Manager build up a visual representation of who is working and when - covering the Implementation Team members only
Imp Runbook | This worksheet contains all the task details associated with the Implementation of the change. Tip: To see only the Checkpoint information, filter on column A.
Backout Runbook | This worksheet contains all the task details associated with the Backout of the change.
Issue Log | All issues associated with the implementation or backout must be recorded in this worksheet. An Issue is defined in this context as any material deviation from the documented tasks. This includes the addition or deletion of a task, any changes to the planned duration and any changes to the defined dependencies. Any technical failure of a task and any remedial activity represents an issue. A significant deviation from the planned duration also represents an issue. If the forecast end time of the implementation reaches 1 hour more than the forecast end time, this must also will be reflected as an issue.
Doc Control | This worksheet provides version control, distribution list information and Implementation Plan approval information
Template Version | v1d0
Date of Issue | 2014-08-08
Issued By | Agenor Technology Limited

## Change Info
Business or Infrastructure Service Affected
Brief Description of Change
Programme Name
Programme Manager
Project Name
Application Project Manager
Infrastructure Project Manager
Conference Call No.
Change Management Records
ITIL Change Record | Change Category | Status | Raised by | Actioned By | Description | Start Date | Start Time | End Date | End Time

## Contacts
Executive Steering Group (ESG) Members | [6 empty] | Contact Numbers(s)
Organisation | Team | Role | Name | Initials | Location | Email | Home (Optional) | Business | Mobile
Implementation Control Group (ICG) Members | [6 empty] | Contact Numbers(s)
Organisation | Team | Role | Name | Initials | Location | Email | Home (Optional) | Business | Mobile
Implementation Management Services (IMS) Members | [6 empty] | Contact Numbers(s)
Organisation | Team | Role | Name | Initials | Location | Email | Home (Optional) | Business | Mobile
Implementation Team Members | [6 empty] | Contact Numbers(s)
Organisation | Team | Role | Name | Initials | Location | Email | Home (?) | Business | Mobile
|  | Implementation Manager | John Doe | JD
|  |  | Joe Bloggs | JB
IT Service Delivery / IT Operations Group
Organisation | Team | Group Mailbox | Landline
Change Management
Incident Management
Change Management
Incident Management
24*7 Operations Centre
Note on E46: Andy Smith: Must be unique

## Roster
Implementation Start Date & Time | 2009-12-09 18:30
Role | Name | Initials | 40156.7708 | 40156.8125 | 40156.8542 | 40156.8958 | 40156.9375 | 40156.9792 | 40157.0208 | 40157.0625 | 40157.1042 | 40157.1458 | 40157.1875 | 40157.2292
Implementation Manager | John Doe | JD
0 | Joe Bloggs | JB
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
Guidelines For Completion | The role, name and initials data is populated directly from the Contacts sheet, reading from the Implementation team only
The implementation start date and time should be entered in the yellow cell - this will populate the times at the top of the roster
The roster assumes a maximum of 12 hours for the implementation - extend as necessary but check that the formulas in row 3 are updated
The roster assumes a maximum of 15 participants in the implementation team -extend as required in the Contacts worksheet and add rows here too
The roster allows a visual representation of who is working when - in 1 hour blocks

## Imp Runbook
Implementation Runbook
2014-09-04 |  |  |  |  | Resources |  |  | Planned Schedule |  |  | Actual Schedule |  |  | Additional Info
Task ID | Dependency | Change Record | Status | Task Description | Task Owner | Team | Role | Start Date & Time | Duration | End Date & Time | Start Date | Duration | End Date | Task Notes
1.1 | 0 |  | Initial |  | AJS | Business Service Mgmt | Implementation Manager | 2009-11-24 23:15 | 0:50 | 2009-11-25 00:05 | 2009-11-24 23:15 | 0:50 | 2009-11-25 00:05
1.2 | 1.1 |  | Initial |  | JB | Midrange Services | Unix Tech Spec | 2009-11-25 00:05 | 0:30 | 2009-11-25 00:35 |  | 0:00
1.3 | 1.2 |  | Initial |  |  |  |  | 2009-11-25 00:35 | 0:10 | 2009-11-25 00:45 |  | 0:00
1.4 | 1.3 |  | Initial |  |  |  |  | 2009-11-25 00:45 | 12:00 | 2009-11-25 12:45 |  | 0:00
1.5 | 1.4 |  | Initial |  |  |  |  | 2009-11-25 12:45 | 12:00 | 2009-11-26 00:45 |  | 0:00
1.6 | 1.5 |  | Initial |  |  |  |  | 2009-11-26 00:45 | 0:05 | 2009-11-26 00:50 |  | 0:00
1.7 | 1.6 |  | Initial |  |  |  |  | 2009-11-26 00:50 | 0:10 | 2009-11-26 01:00 |  | 0:00
1.8 | 1.7 |  | Initial |  |  |  |  | 2009-11-26 01:00 | 0:15 | 2009-11-26 01:15 |  | 0:00
1.9 | 1.8 |  | Initial |  |  |  |  | 2009-11-26 01:15 | 0:30 | 2009-11-26 01:45 |  | 0:00
1.1 | 1.9 |  | Initial |  |  |  |  | 2009-11-26 01:45 | 0:10 | 2009-11-26 01:55 |  | 0:00
Checkpoint 1 | [7 empty] | 2009-11-26 01:55 | 0:05 | 2009-11-26 02:00 |  | 0:00
Task ID | Dependency | Change Record | Status | Task Description | Task Owner | Team | Role | Start Date | Duration | End Date | Start Date | Duration | End Date | Task Notes
2.1 | 1.1 |  | Initial |  |  |  |  | 2009-11-26 02:00 | 0:10 | 2009-11-26 02:10 |  | 0:00
2.2 | 2.1 |  | Initial |  |  |  |  | 2009-11-26 02:10 | 0:20 | 2009-11-26 02:30 |  | 0:00
2.3 | 2.2 |  | Initial |  |  |  |  | 2009-11-26 02:30 | 0:10 | 2009-11-26 02:40 |  | 0:00
2.4 | 2.3 |  | Initial |  |  |  |  | 2009-11-26 02:40 | 0:10 | 2009-11-26 02:50 |  | 0:00
2.5 | 2.4 |  | Initial |  |  |  |  | 2009-11-26 02:50 | 0:10 | 2009-11-26 03:00 |  | 0:00
2.6 | 2.5 |  | Initial |  |  |  |  | 2009-11-26 03:00 | 0:10 | 2009-11-26 03:10 |  | 0:00
2.7 | 2.6 |  | Initial |  |  |  |  | 2009-11-26 03:10 | 0:10 | 2009-11-26 03:20 |  | 0:00
2.8 | 2.7 |  | Initial |  |  |  |  | 2009-11-26 03:20 | 0:10 | 2009-11-26 03:30 |  | 0:00
2.9 | 2.8 |  | Initial |  |  |  |  | 2009-11-26 03:30 | 0:10 | 2009-11-26 03:40 |  | 0:00
2.2 | 2.9 |  | Initial |  |  |  |  | 2009-11-26 03:40 | 0:10 | 2009-11-26 03:50 |  | 0:00
Checkpoint 2 | [7 empty] | 2009-11-26 03:50 | 0:05 | 2009-11-26 03:55 |  | 0:00
Task ID | Dependency | Change Record | Status | Task Description | Task Owner | Team | Role | Start Date | Duration | End Date | Start Date | Duration | End Date | Task Notes
3.1 | 2.2 |  | Initial |  |  |  |  | 2009-11-26 03:55 | 0:10 | 2009-11-26 04:05 |  | 0:00
3.2 | 3.1 |  | Initial |  |  |  |  | 2009-11-26 04:05 | 0:10 | 2009-11-26 04:15 |  | 0:00
3.3 | 3.2 |  | Initial |  |  |  |  | 2009-11-26 04:15 | 0:10 | 2009-11-26 04:25 |  | 0:00
3.4 | 3.3 |  | Initial |  |  |  |  | 2009-11-26 04:25 | 0:10 | 2009-11-26 04:35 |  | 0:00
3.5 | 3.4 |  | Initial |  |  |  |  | 2009-11-26 04:35 | 0:10 | 2009-11-26 04:45 |  | 0:00
3.6 | 3.5 |  | Initial |  |  |  |  | 2009-11-26 04:45 | 0:10 | 2009-11-26 04:55 |  | 0:00
3.7 | 3.6 |  | Initial |  |  |  |  | 2009-11-26 04:55 | 0:10 | 2009-11-26 05:05 |  | 0:00
3.8 | 3.7 |  | Initial |  |  |  |  | 2009-11-26 05:05 | 0:10 | 2009-11-26 05:15 |  | 0:00
3.9 | 3.8 |  | Initial |  |  |  |  | 2009-11-26 05:15 | 0:10 | 2009-11-26 05:25 |  | 0:00
3.1 | 3.9 |  | Initial |  |  |  |  | 2009-11-26 05:25 | 0:10 | 2009-11-26 05:35 |  | 0:00
Checkpoint 3 | [7 empty] | 2009-11-26 05:35 | 0:05 | 2009-11-26 05:40 |  | 0:00
Task ID | Dependency | Change Record | Status | Task Description | Task Owner | Team | Role | Start Date | Duration | End Date | Start Date | Duration | End Date | Task Notes
4.1 | 3.1 |  | Initial |  |  |  |  | 2009-11-26 05:40 | 0:10 | 2009-11-26 05:50 |  | 0:00
4.2 | 4.1 |  | Initial |  |  |  |  | 2009-11-26 05:50 | 0:10 | 2009-11-26 06:00 |  | 0:00
4.3 | 4.2 |  | Initial |  |  |  |  | 2009-11-26 06:00 | 0:10 | 2009-11-26 06:10 |  | 0:00
4.4 | 4.3 |  | Initial |  |  |  |  | 2009-11-26 06:10 | 0:10 | 2009-11-26 06:20 |  | 0:00
4.5 | 4.4 |  | Initial |  |  |  |  | 2009-11-26 06:20 | 0:10 | 2009-11-26 06:30 |  | 0:00
4.6 | 4.5 |  | Initial |  |  |  |  | 2009-11-26 06:30 | 0:10 | 2009-11-26 06:40 |  | 0:00
4.7 | 4.6 |  | Initial |  |  |  |  | 2009-11-26 06:40 | 0:10 | 2009-11-26 06:50 |  | 0:00
4.8 | 4.7 |  | Initial |  |  |  |  | 2009-11-26 06:50 | 0:10 | 2009-11-26 07:00 |  | 0:00
4.9 | 4.8 |  | Initial |  |  |  |  | 2009-11-26 07:00 | 0:10 | 2009-11-26 07:10 |  | 0:00
4.1 | 4.9 |  | Initial |  |  |  |  | 2009-11-26 07:10 | 0:10 | 2009-11-26 07:20 |  | 0:00
Checkpoint 4 | [7 empty] | 2009-11-26 07:20 | 0:05 | 2009-11-26 07:25 |  | 0:00
Guidelines For Completion |  | The Task Owner, Role and team drop downs are driven from the Contacts worksheet, reading from the Implementation team only
The implementation start date and time should be entered in the yellow cell - this will represent the reference point for scheduling the remainder of the Runbook
The only other field to edit is the duration field for each task - assuming a sequential dependency default
If dependencies are not sequential, the time arithmetic must be manually edited
Please note that Pre and Post Implementation activities must be scheduled manually
For the Actual Schedule time fields, please enter the actual start date/time and actual end date/time. The duration becomes a calculated field
Formulas:
End Date & Time = [Planned Schedule]+[Duration]
Actual Schedule = [Planned Schedule]
End Date = [End Date & Time]
Planned Schedule = [End Date & Time, row above]
Note on J11: Andy Smith: HH:MM
Note on K11: Andy Smith: DD/MM/YYYY
Note on L11: Andy Smith: DD/MM/YYYY
Note on M11: Andy Smith: HH:MM
Note on N11: Andy Smith: DD/MM/YYYY
Note on I23: Andy Smith: DD/MM/YYYY
Note on J23: Andy Smith: HH:MM
Note on K23: Andy Smith: DD/MM/YYYY
Note on L23: Andy Smith: DD/MM/YYYY
Note on M23: Andy Smith: HH:MM
Note on N23: Andy Smith: DD/MM/YYYY
Note on I35: Andy Smith: DD/MM/YYYY
Note on J35: Andy Smith: HH:MM
Note on K35: Andy Smith: DD/MM/YYYY
Note on L35: Andy Smith: DD/MM/YYYY
Note on M35: Andy Smith: HH:MM
Note on N35: Andy Smith: DD/MM/YYYY
Note on I47: Andy Smith: DD/MM/YYYY
Note on J47: Andy Smith: HH:MM
Note on K47: Andy Smith: DD/MM/YYYY
Note on L47: Andy Smith: DD/MM/YYYY
Note on M47: Andy Smith: HH:MM
Note on N47: Andy Smith: DD/MM/YYYY

## Backout Runbook
Backout Runbook
Task Information |  |  |  |  | Resources |  |  | Planned Schedule |  |  | Actual Schedule |  |  | Additional Info
Task ID | Dependency | Change Record | Status | Task Description | Task Owner | Team | Role | Start Date & Time | Duration | End Date & Time | Start Date | Duration | End Date | Task Notes
1.1 | 0 |  | Initial |  | AJS | Business Service Mgmt | Implementation Manager | 2009-11-24 23:15 | 0:50 | 2009-11-25 00:05 | 2009-11-24 23:15 | 0:50 | 2009-11-25 00:05
1.2 | 1.1 |  | Initial |  | JB | Midrange Services | Unix Tech Spec | 2009-11-25 00:05 | 0:30 | 2009-11-25 00:35 |  | 0:00
1.3 | 1.2 |  | Initial |  |  |  |  | 2009-11-25 00:35 | 0:10 | 2009-11-25 00:45 |  | 0:00
1.4 | 1.3 |  | Initial |  |  |  |  | 2009-11-25 00:45 | 12:00 | 2009-11-25 12:45 |  | 0:00
1.5 | 1.4 |  | Initial |  |  |  |  | 2009-11-25 12:45 | 12:00 | 2009-11-26 00:45 |  | 0:00
1.6 | 1.5 |  | Initial |  |  |  |  | 2009-11-26 00:45 | 0:05 | 2009-11-26 00:50 |  | 0:00
1.7 | 1.6 |  | Initial |  |  |  |  | 2009-11-26 00:50 | 0:10 | 2009-11-26 01:00 |  | 0:00
1.8 | 1.7 |  | Initial |  |  |  |  | 2009-11-26 01:00 | 0:15 | 2009-11-26 01:15 |  | 0:00
1.9 | 1.8 |  | Initial |  |  |  |  | 2009-11-26 01:15 | 0:30 | 2009-11-26 01:45 |  | 0:00
1.1 | 1.9 |  | Initial |  |  |  |  | 2009-11-26 01:45 | 0:10 | 2009-11-26 01:55 |  | 0:00
Checkpoint 1 | [7 empty] | 2009-11-26 01:55 | 0:05 | 2009-11-26 02:00 |  | 0:00
Task ID | Dependency | Change Record | Status | Task Description | Task Owner | Team | Role | Start Date | Duration | End Date | Start Date | Duration | End Date | Task Notes
2.1 | 1.1 |  | Initial |  |  |  |  | 2009-11-26 02:00 | 0:10 | 2009-11-26 02:10 |  | 0:00
2.2 | 2.1 |  | Initial |  |  |  |  | 2009-11-26 02:10 | 0:20 | 2009-11-26 02:30 |  | 0:00
2.3 | 2.2 |  | Initial |  |  |  |  | 2009-11-26 02:30 | 0:10 | 2009-11-26 02:40 |  | 0:00
2.4 | 2.3 |  | Initial |  |  |  |  | 2009-11-26 02:40 | 0:10 | 2009-11-26 02:50 |  | 0:00
2.5 | 2.4 |  | Initial |  |  |  |  | 2009-11-26 02:50 | 0:10 | 2009-11-26 03:00 |  | 0:00
2.6 | 2.5 |  | Initial |  |  |  |  | 2009-11-26 03:00 | 0:10 | 2009-11-26 03:10 |  | 0:00
2.7 | 2.6 |  | Initial |  |  |  |  | 2009-11-26 03:10 | 0:10 | 2009-11-26 03:20 |  | 0:00
2.8 | 2.7 |  | Initial |  |  |  |  | 2009-11-26 03:20 | 0:10 | 2009-11-26 03:30 |  | 0:00
2.9 | 2.8 |  | Initial |  |  |  |  | 2009-11-26 03:30 | 0:10 | 2009-11-26 03:40 |  | 0:00
2.2 | 2.9 |  | Initial |  |  |  |  | 2009-11-26 03:40 | 0:10 | 2009-11-26 03:50 |  | 0:00
Checkpoint 2 | [7 empty] | 2009-11-26 03:50 | 0:05 | 2009-11-26 03:55 |  | 0:00
Task ID | Dependency | Change Record | Status | Task Description | Task Owner | Team | Role | Start Date | Duration | End Date | Start Date | Duration | End Date | Task Notes
3.1 | 2.2 |  | Initial |  |  |  |  | 2009-11-26 03:55 | 0:10 | 2009-11-26 04:05 |  | 0:00
3.2 | 3.1 |  | Initial |  |  |  |  | 2009-11-26 04:05 | 0:10 | 2009-11-26 04:15 |  | 0:00
3.3 | 3.2 |  | Initial |  |  |  |  | 2009-11-26 04:15 | 0:10 | 2009-11-26 04:25 |  | 0:00
3.4 | 3.3 |  | Initial |  |  |  |  | 2009-11-26 04:25 | 0:10 | 2009-11-26 04:35 |  | 0:00
3.5 | 3.4 |  | Initial |  |  |  |  | 2009-11-26 04:35 | 0:10 | 2009-11-26 04:45 |  | 0:00
3.6 | 3.5 |  | Initial |  |  |  |  | 2009-11-26 04:45 | 0:10 | 2009-11-26 04:55 |  | 0:00
3.7 | 3.6 |  | Initial |  |  |  |  | 2009-11-26 04:55 | 0:10 | 2009-11-26 05:05 |  | 0:00
3.8 | 3.7 |  | Initial |  |  |  |  | 2009-11-26 05:05 | 0:10 | 2009-11-26 05:15 |  | 0:00
3.9 | 3.8 |  | Initial |  |  |  |  | 2009-11-26 05:15 | 0:10 | 2009-11-26 05:25 |  | 0:00
3.1 | 3.9 |  | Initial |  |  |  |  | 2009-11-26 05:25 | 0:10 | 2009-11-26 05:35 |  | 0:00
Checkpoint 3 | [7 empty] | 2009-11-26 05:35 | 0:05 | 2009-11-26 05:40 |  | 0:00
Task ID | Dependency | Change Record | Status | Task Description | Task Owner | Team | Role | Start Date | Duration | End Date | Start Date | Duration | End Date | Task Notes
4.1 | 3.1 |  | Initial |  |  |  |  | 2009-11-26 05:40 | 0:10 | 2009-11-26 05:50 |  | 0:00
4.2 | 4.1 |  | Initial |  |  |  |  | 2009-11-26 05:50 | 0:10 | 2009-11-26 06:00 |  | 0:00
4.3 | 4.2 |  | Initial |  |  |  |  | 2009-11-26 06:00 | 0:10 | 2009-11-26 06:10 |  | 0:00
4.4 | 4.3 |  | Initial |  |  |  |  | 2009-11-26 06:10 | 0:10 | 2009-11-26 06:20 |  | 0:00
4.5 | 4.4 |  | Initial |  |  |  |  | 2009-11-26 06:20 | 0:10 | 2009-11-26 06:30 |  | 0:00
4.6 | 4.5 |  | Initial |  |  |  |  | 2009-11-26 06:30 | 0:10 | 2009-11-26 06:40 |  | 0:00
4.7 | 4.6 |  | Initial |  |  |  |  | 2009-11-26 06:40 | 0:10 | 2009-11-26 06:50 |  | 0:00
4.8 | 4.7 |  | Initial |  |  |  |  | 2009-11-26 06:50 | 0:10 | 2009-11-26 07:00 |  | 0:00
4.9 | 4.8 |  | Initial |  |  |  |  | 2009-11-26 07:00 | 0:10 | 2009-11-26 07:10 |  | 0:00
4.1 | 4.9 |  | Initial |  |  |  |  | 2009-11-26 07:10 | 0:10 | 2009-11-26 07:20 |  | 0:00
Checkpoint 4 | [7 empty] | 2009-11-26 07:20 | 0:05 | 2009-11-26 07:25 |  | 0:00
Guidelines For Completion |  | The Task Owner, Role and team drop downs are driven from the Contacts worksheet, reading from the Implementation team only
The implementation start date and time should be entered in the yellow cell - this will represent the reference point for scheduling the remainder of the Runbook
The only other field to edit is the duration field for each task - assuming a sequential dependency default
If dependencies are not sequential, the time arithmetic must be manually edited
Please note that Pre and Post Implementation activities must be scheduled manually
For the Actual Schedule time fields, please enter the actual start date/time and actual end date/time. The duration becomes a calculated field
Formulas:
End Date & Time = [Planned Schedule]+[Duration]
Actual Schedule = [Planned Schedule]
End Date = [End Date & Time]
Planned Schedule = [End Date & Time, row above]
Note on J10: Andy Smith: HH:MM
Note on K10: Andy Smith: DD/MM/YYYY
Note on L10: Andy Smith: DD/MM/YYYY
Note on M10: Andy Smith: HH:MM
Note on N10: Andy Smith: DD/MM/YYYY
Note on I22: Andy Smith: DD/MM/YYYY
Note on J22: Andy Smith: HH:MM
Note on K22: Andy Smith: DD/MM/YYYY
Note on L22: Andy Smith: DD/MM/YYYY
Note on M22: Andy Smith: HH:MM
Note on N22: Andy Smith: DD/MM/YYYY
Note on I34: Andy Smith: DD/MM/YYYY
Note on J34: Andy Smith: HH:MM
Note on K34: Andy Smith: DD/MM/YYYY
Note on L34: Andy Smith: DD/MM/YYYY
Note on M34: Andy Smith: HH:MM
Note on N34: Andy Smith: DD/MM/YYYY
Note on I46: Andy Smith: DD/MM/YYYY
Note on J46: Andy Smith: HH:MM
Note on K46: Andy Smith: DD/MM/YYYY
Note on L46: Andy Smith: DD/MM/YYYY
Note on M46: Andy Smith: HH:MM
Note on N46: Andy Smith: DD/MM/YYYY

## Issue Log
Issue Log
ID | Issue Number | Date Raised | Time Raised | Raised By | Issue Owner | Runbook Task ID | Issue Severity | Issue Description | Actions Taken | Action By | Issue Status | Date Closed | Time Closed | Closed By
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Doc Control
Document Set | Runbook - This document
Technical Implementation Plan
Release Definition Document
Version Control
Version | Description | Author | Status | Date
Circulation
Organisation | Team | Role | Person | Purpose
Approval Tracking
Organisation | Team | Role | Person | Status | Date
©
Note on C7: Andy X Smith: Insert hyperlink here
Note on C8: Andy X Smith: Insert hyperlink here
Note on C9: Andy X Smith: Insert hyperlink here