## Log (hidden)
GEN-SET START-UP CHECKLIST
Project | Contractor | POC | Email POC | Phone POC | Date Sent | Visit Date | Tech Visit | Salesman
Capital Caring | Austin Taylor Electric | Charles Grabis Jr. | charles@austintaylor llc.com | 240-687-3034 | 2016-09-06 | 2016-09-12 | 2016-09-13 | Paul
Lake Ridge MS | Mackey Electrical | Jason Mackey | mackey@mackeyelectric.net | 240-882-7244 | 2016-09-06 |  |  | Alan
New Hampshire ES | Amber Enterprises | Craig Kienast | craig@ambercontractors.com | 240-464-6956 | 2016-09-08 | 2016-09-14 | 2016-09-16 | Alan
Woodfield ES | Amber Enterprises | Craig Kienast | craig@ambercontractors.com | 240-464-6956 | 2016-09-08 | 2016-09-14 |  | Alan
Neelsville ES | Amber Enterprises | Craig Kienast | craig@ambercontractors.com | 240-464-6956 | 2016-09-08 | 2016-09-14 |  | Alan
U of Deleware | Nickle Electrical Co | Brian Stump | bstump@nickle.email | 410-365-2494 | 2016-09-08 | 2016-09-22 | 2016-09-27 | Alan
Maryland Manor | Water Services | Ed Crooks | ecc989@hotmail.com | 410-353-0383 | 2016-09-09 |  |  | Alan
Conifer @ Oakcrest | Colonial Electric | Luis Palencia |  | 443-336-4498 | 2016-09-07 | 2016-09-13 | 2016-09-14 | Alan
Cloverly ES | Amber Enterprises | Craig Kienast | craig@ambercontractors.com | 240-464-6956 | 2016-09-20 | 2016-09-29 | 2016-09-29 | Alan
Laytonsville ES | Amber Enterprises | Craig Kienast | craig@ambercontractors.com | 240-464-6956 | 2016-09-20 | 2016-09-29 | 2016-09-29 | Alan

## Check List (hidden)
GENERATOR SET START-UP CHECKLIST
Requested Date: |  | Requested Time:
Sales Person: |  | Generator Location:
Job Name: |  | Address:
Contractor: |  | City & State:
Contact Name: |  | Owner's Name:
Contact Phone #: |  | Owner's Phone #:
Generator Model #: |  | Load Bank Test Hrs.:
Generator Serial #: |  | Engine Make/Model:
Generator Voltage: |  | Turn Key Project:
Generator kW: |  | 1 Phase or 3 Phase:
Warranty and Maintenance
Warranty Duration in Years:
Maintenance Contract Included with Sale:
Contract Type (semi-annual or quarterly):
Contact for Warranty and Maintenance:
Miscellaneous Warranty and Maintenance Info:
Unit is set in place on vibration pads and secure with floor and anchor/studs.
All air ducting and louver installation is complete and functioning.
If diesel, is there 50% fuel supply in the tank for start-up and load bank testing, if required
If,natural gas is the system complete and inspected.
Is the load wiring terminated; wheather power or control the conductors must stranded.
Any additional controls/alarms to be wired/Remote Annunciator?
The exhaust system is complete and operational.
The block heater is connected to proper voltage and circuit is not energized.
The Technician will energize the block heater.
Battery Charger is mounted w/ AC and DC wired (if not supplied & mounted by factory).
Normal power is available at the ATS and Building load is available for testing.
The Gen-Set is not starting under any load. If so an emergency contactor may need to be installed.
The Generator Set area is clean and free of all dirt and debris prior to start of engine.
Is parking available for technician?
Are cell phones allowed onsite?
Length of Loadbank cables
Is training required on the date of the startup? If so, how long?
The end user and /or owners have been notified to be available at the initial start-up.
This will be the only demonstration by Curtis Engine unless otherwise requested.
If the owner is nor available, the Contractor will be responsible any training.
Have any discrepancy been brought to the attention of Curtis Engine prior to start-up.
Authorized Signature: Date:
Please email this form to cjinadu@curtisengine.com to schedule a start-up one week in advance.
If the technician arrives at the site for scheduled start up and the generator is not
If the Owners are not available for the start-up demonstration, the Contractor will then be Responsible for any training.

## Start-UP Checklist
COMPLETE AND EMAIL 10 WORKING DAYS PRIOR TO START-UP
Start-Up Date: |  | Tech @ Phone #:
Sales Person: |  | Project Name:
Customer: |  | Address:
Site Contact Name: |  | City, State, Zip Code:
Site Contact Phone #: |  | Owner's Name:
Site Contact Email: |  | Address:
Generator Location: |  | City, State, Zip Code:
Generator Model #: |  | Phone #:
Generator Serial #: |  | Engine Model #:
Generator kW: |  | ATS Amps & S/N:
Generator Voltage: |  | Load Bank Test:
Generator Phase: |  | Test Cable Length:
WARRANTY AND MAINTENANCE INFORMATION
Manufacturer's Standard Warranty Duration:
Maintenance Contract Included with Sale:
Contract Type-Annual, Semi-Annual, Monthly, Quarterly:
Owner's Contact Name & Phone Number:
Miscellaneous Warranty and Maintenance Info:
ANSWERS
YES NO N/A | Is the Gen-Set set in place either on vibration pads or spring isolators and is secured with anchors?
YES NO N/A | Have the spring isolators been adjusted?
YES NO N/A | Is the Gen-Set area is clean and free of all dirt and debris inside and around the unit?
YES NO N/A | Is there 75% of #2 ultra low sulfur diesel fuel available in the tank for start-up and load bank testing?
YES NO N/A | Are the fuel lines from the Main Tank to the Day Tank, filled, primed and check valve installed?
YES NO N/A | Is the gas fuel piping sized correctly, with a flex line, has been pressure tested and inspected?
ANSWERS
YES NO N/A | Is the air ducting, louvers and exhaust installation complete and wired?
YES NO N/A | If this is an open Gen-Set Unit, does the discharge cooling air exhaust from the radiator side?
YES NO N/A | Is a 2 conductor, shielded cable and a D/C or A/C power supply for the mounted Remote Annunciator?
YES NO N/A | Any additional control/alarm circuits pulled, labeled to be terminated in the ATS(s)?
YES NO N/A | Are the D/C control cable(s) stranded, labeled to be terminated and in a separate conduit?
YES NO N/A | Is the block heater and battery charger wired and labeled? (DO NOT ENERGIZE)
YES NO N/A | Is normal / utility power available at the ATS(s) for building load testing?
YES NO N/A | Does the Gen-Set and ATS(s) match the building voltage?
YES NO N/A | Is the ATS(s) properly grounded / bonded?
YES NO N/A | Are there any dedicated 20 amp receptacle circuits available for the load bank testing?
YES NO N/A | Are the O&M's, battery cables, exhaust parts, etc. items received and on site?
YES NO N/A | Is parking available close to the Gen-Set and the ATS(s) for the technician?
YES NO N/A | Is safety training and or personal safety protection required prior to the technician working on site?
YES NO N/A | Is a security clearance required; If so, is there an escort available?
YES NO N/A | Are cell phones and other electronic devices allowed on-site?
YES NO N/A | Has the end user and /or owners have been notified to be available for training at the initial start-up?
YES NO N/A | If the end user is not available, will the Contractor be responsible for the demonstrations and training?
YES NO N/A | Have other arrangements been made in advance for any additional training by Curtis Engine?
YES NO N/A | Have any discrepancy or issues been brought to the attention of Curtis Engine prior to start-up?
IF THE GEN-SET IS NOT READY AT THE TIME OF THE START-UP, ADDITIONAL COST MAY BE INCURRED
Additional Notes: All conductors must be stranded.
Signature: Print Name: |  |  | Date: